## Sheet1
TestName | Step | Expected Result | TestName |  | Estimate (hours/mins)
TC-01 Create Account | Click Sign In | Sign In Form Displayed | TC-01 Create Account | - | M | S | 2-3 hours | 2 | 3
(Simple Test. Additional Time added for setup and config of framework for scripting.)
| Click No account? Create one here | Account Creation Form is displayed | TC-02 Validate Discount | - | S | M | 3-8 hours | 3 | 8
(Simple Test. Build on what was created from Test 1)
| Complete the form and save | Account should be logged in automatically after creation | TC-03 Search | - | M | L | 8-16 hours | 8 | 16
(New pages / functionality to script. Script with re-use in mind)
| Sign Out | Sign In link should be visible | TC-04 Search | - | S | XL | 16 + hours
(Re-use TC-03 with different data)
| Sign Back in using the new account | Account sign in should be successful | TC-05 Add Item to Cart | - | L | Totals |  | 18 | 38
(Largest Test case. Additional Pages added. More time allocated.)
TC-02 Validate Discount | Navigate to homepage | homepage is displayed
| Validate Price for Hummingbird Printed T-Shirt | R21.80
| Validate Original price for Hummingbird Printed T-Shirt | R27.25 | Time Estimation: 2xM, 2xS
| Validate Discount on Hummingbird Printed T-Shirt | -20%
| Ensure that the difference between Original Price and Current price is equal to the presented discount | -20%
TC-03 Search | Navigate to homepage | homepage is displayed
| Search for Hummingbird Printed T-Shirt | Search Results page is displayed with 8 products
| Validate Price for Hummingbird Printed T-Shirt | R21.80
| Validate Original price for Hummingbird Printed T-Shirt | R27.25
| Validate Discount on Hummingbird Printed T-Shirt | -20%
| Ensure that the difference between Original Price and Current price is equal to the presented discount | -20%
TC-04 Search | Navigate to homepage | homepage is displayed
| Search for Hummingbird Printed Sweater | Search Results page is displayed with 8 products
| Validate Price for Hummingbird Printed Sweater | R32.74
| Validate Original price for Hummingbird Printed Sweater | R40.93
| Validate Discount on Hummingbird Printed Sweater | -20%
| Ensure that the difference between Original Price and Current price is equal to the presented discount | -20%
TC-05 Add Item to Cart | Navigate to homepage | homepage is displayed
| Select Clothes -> Women | Womens Clothes section is displayed with 1 item
| Select Hummingbird Printed Sweater | Item page is loaded
| Validate Price for Hummingbird Printed Sweater | R32.74
| Validate Original price for Hummingbird Printed Sweater | R40.93
| Validate Discount on Hummingbird Printed Sweater | -20%
| Add 1 item to cart | Product succesfully added to cart notification appears
| Click Proceed to checkout | Cart page loaded, Cart icon in corner should say Cart(1) your item should be in the cart
| Click the bin icon to remove the item from the cart | Page should say - There are no more items in your cart
The Icon in the corner should say Cart(0)